## Blad1
Activity | Start date | Enddate | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
Writing project report | 2016-02-08 | 2016-02-14 |  |  |  | Writing project report
Writing project plan report | 2016-01-19 | 2016-02-11 | Writing project plan report
Deadline: Hand in of project plan document | 2016-02-12 | 2016-02-12 |  |  |  | Deadline: Hand in of project plan document
Gathering & processing training/validation data | 2016-02-08 | 2016-02-28 |  |  |  | Gathering & processing training/validation data
Prestudy | 2016-01-19 | 2016-02-05 | Prestudy
Implementation (random headline) | 2016-02-08 | 2016-02-28 |  |  |  | Implementation (random headline)
Implementation (headlines based on text) | 2016-02-15 | 2016-04-22 |  |  |  |  | Implementation (headlines based on text)
Hyperparameter optimization | 2016-02-15 | 2016-04-22 |  |  |  |  | Hyperparameter optimization
Possibly implementation of attention model | 2016-03-07 | 2016-04-22 | [7 empty] | Possibly implementation of attention model
Creating program for exhibition (if time left) | 2016-04-25 | 2016-05-01 | [14 empty] | Creating program for exhibition (if time left)
Preparing half time presentation | 2016-02-22 | 2016-02-29 | [5 empty] | Preparing half time presentation
Half time presentation (oral) | 2016-03-01 | 2016-03-01 | [6 empty] | Half time presentation (oral)
Deadline: Hand in of personal report (form) | 2016-03-11 | 2016-03-11 | [7 empty] | Deadline: Hand in of personal report (form)
Deadline: Hand in of project report | 2016-05-16 | 2016-05-16 | [16 empty] | Deadline: Hand in of project report
Preparing exhibition of project outcome | 2016-05-09 | 2016-05-15 | [16 empty] | Preparing exhibition of project outcome
Exhibition of project outcome | 2016-05-17 | 2016-05-17 | [17 empty] | Exhibition of project outcome
Deadline: Hand in of personal report (form) | 2016-05-27 | 2016-05-27 | [18 empty] | Deadline: Hand in of personal report (form)
Preparing final presentation | 2016-05-16 | 2016-05-25 | [17 empty] | Preparing final presentation
Writing opposition | 2016-05-16 | 2016-05-25 | [17 empty] | Writing opposition
Final presentation and opposition (oral) | 2016-05-26 | 2016-05-27 | [18 empty] | Final presentation and opposition (oral)
Adding opposition comments to project report | 2016-05-28 | 2016-06-01 | [19 empty] | Adding opposition comments to project report
Deadline: Project report w/ opposition comments | 2016-06-01 | 2016-06-01 | [19 empty] | Deadline: Project report w/ opposition comments